## Slide 1: Hybrid Cloud Program– Phase II TCS Approach
TCS – Fifth Third- Confidential

## Slide 2
Agenda
TCS – Fifth Third Bank Confidential
Hybrid Cloud Roadmap
Phase II – Work streams
  Work stream 1 – Infrastructure as a code
  Work stream 2 – Private Cloud Platform Build
  Work stream 3 – AWS Build
  Work stream 4 &5 – PaaS & CaaS Build

## Slide 3
Ph.-II Decisions
& PaaS PoC
Hybrid Cloud – Road Map
TCS – Fifth Third Bank Confidential
M-1 to M-6
M-12 & Beyond
Phase I
Hybrid Cloud - Platform Design
Work stream 1 – Hybrid Cloud Technology Platform Design - HLD & LLD
Work stream 2 – Hybrid Cloud Security Requirements
Work stream 3 – Hybrid Cloud Process Design
Work stream 4 – OCM
Work stream 5 – Application Assessment
Status : On Track, Targeted for June 16 Completion & Sign-Off
Phase II
Hybrid Cloud – Platform Engineering
Phase III
New App Dev. & Migration
Infrastructure as a Code
We are here
Private Cloud Platform Build
AWS Build
PaaS and CaaS Build
New application development on the hybrid cloud platform
Migrate existing applications suitable to the hybrid cloud platform
Consume hybrid cloud service catalog
Continue platform enhancement with new features addition & automation
Add additional cloud providers like Azure to the hybrid cloud platform
Software Defined Networking
Software Defined Storage
M7
M12
M10
M11
M8
M9

## Slide 4
Phase II - Work stream 1 – Infrastructure as a Code – Activities
TCS – Fifth Third Bank Confidential
S No. | Module | Activities
1 | Tooling Deployment | Select Toolset for the Automation Platform Proof of Concepts as needed (Orchestration Platform, Infrastructure blueprinting) Deploy image build / patching tool Deploy CI/CD Toolset - Code commit & versioning, build, deploy and test Deploy Endpoint Configuration Management toolset Implement build, release and deploy pipeline
2 | Develop, Test and Deploy | OS Image build (Windows & Linux) Linux server provisioning (On-Premises + AWS) Windows server provisioning (On-Premises + AWS) Platform Software package build (web server, App server, Database) Post VM provisioning (Platform software install – Web and App server) - Windows Post VM provisioning (Platform software install – Web and App server) – Linux Platform Software package build (MQ) Post VM provisioning (Platform software install – MQ) On-Premises – VM - storage capacity resizing (ad-hoc) On-Premises - VM - compute capacity resizing (ad-hoc) Post VM provisioning (Platform software install – Database) Automation of server decommission (On-Premises + AWS) Automatic reconciliation of servers into monitoring and backup DNS and IPAM automation (provision / de-provision)

## Slide 5
Phase II - Work stream 1 – Infrastructure as a Code – Activities
TCS – Fifth Third Bank Confidential
S No. | Module | Activities
3 | Cloud processes (new) | Select tools for implementing new cloud processes Tool deployment and process configuration Integration with existing IT processes
4 | Cloud processes (existing) | Enhance existing processes as per design Modify current tools (ITSM) for process implementation

## Slide 6
Phase II - Work stream 1 – Infrastructure as a Code – Timelines, Resources
TCS – Fifth Third Bank Confidential
Activity Stream
Estimated Timelines & Milestone
Resourcing (per activity stream/ module)
Resource Profile
Onsite
Offshore
1 M
Automation Engineer
2.25
4.5
Module 1 : Tooling Deployment
Module 2 : Develop, Test and Deploy
4 Months
Automation Architect
1 M
Time lines ::
6 Months
Total Resources ::
13.5 person months
27 person months
MS1
MS2
M9
M12
MS1
Automation platform build & OS image build
Automation of Platform software (web server) install
Platform Software package build (App server)
Windows server provisioning
Linux server provisioning (AWS + On-Premises)
Platform Software package build (web server)
Establish new cloud processes
MS2
Automation of Platform software (App) install for Windows and Linux
Automation of On-Premises VM resource resizing (Compute and Storage)
Platform software package build (Database & MQ)
Automation of Platform software install (Database & MQ)
Automation of server decommission (On-Premises + AWS)
Automatic reconciliation of servers into monitoring and backup
DNS and IPAM automation (provision / de-provision)
Process Consultant

## Slide 7
Phase II - Work stream 2 – Private Cloud Platform Build – Activities
TCS – Fifth Third Bank Confidential
S No. | Module | Activities
1 | Private Cloud Platform Build | Install and configure ESXi hosts (on primary and DR) Install and configure Virtualization Management - vCenter Configure virtual DCs Configure ESX clusters Configure Backend storage and Data stores on the virtualization layer Configure Virtual networking Install and configure foundation services - AD, DNS, IPAM, Antivirus, Patch Management, Backup, logging, remote connectivity etc. Create VMware golden image Templates based on JEOS, Hybrid images Setup monitoring, logging etc. for the private cloud platform Platform testing Follow change management guidelines and go-live

## Slide 8
Phase II - Work stream 2 – Private Cloud Platform Build – Activities
TCS – Fifth Third Bank Confidential
S No. | Module | Activities
2 | Operating Model | Develop skill matrix for target state operating model (based on technology / tool selection) Publish core messages (for the hybrid cloud program) to the identified stakeholders Evaluate current IT team skills to identify skill gap and training needs Map current IT team to target state operating model & configure the IT process toolset accordingly Identify resourcing requirement for the unfulfilled roles (target state) Establish training and resourcing plan for target state operating model Communicate re-org changes to relevant stakeholders

## Slide 9
Phase II - Work stream 2 – Private Cloud Build – Timelines, Resources
TCS – Fifth Third Bank Confidential
Activity Stream
Estimated Timelines
Resourcing (per activity stream/ module)
Module 1 : Private Cloud Platform Build
Resource Profile
Onsite
Offshore
4 Months
Cloud Engineer
1.25
3.5
Time lines ::
4 Months
Total Resources ::
5 person months
14 person months
MS1
MS1
On-Premises private cloud compute platform build (Primary and secondary datacenter)
Storage and Virtual Network configured (Primary and secondary datacenter)
Enhance existing cloud processes
MS2
MS2
Foundation services deployed (AD, DNS, IPAM, Antivirus, Patch Management, Backup, Logging, Remote connectivity)
Platform testing
Platform go-live
M8
M10

## Slide 10
Phase II - Work stream 3 – AWS Build – Activities
TCS – Fifth Third Bank Confidential
S No. | Module | Activities
1 | AWS Build | AWS Account setup IAM accounts setup – user, groups and roles IAM Access policies setup VPCs setup – VPC, Subnets, NACL, Security groups, Route tables, IGWs etc. Establish On premises to AWS Connectivity Setup EC2 AMIs – JEOS, hybrid and full baked AMIs Setup Foundational services – AD, DNS, Patching, Antivirus, monitoring, logging, backup etc. IAM accounts federated identity with on premises identity store setup Enable AWS monitoring, logging services AWS KMS and encryption policies setup Control policies and scripts setup for cost optimization Setup automation policies via Infrastructure as a code Build Documentation Validation & Testing Security validation and testing and sign-off

## Slide 11
Phase II - Work stream 3 – AWS Build – Timelines, Resources
TCS – Fifth Third Bank Confidential
Activity Stream
Estimated Timelines
Resourcing (per activity stream/ module)
Module 1 : AWS Platform Build & Foundational Services build on AWS Platform
Resource Profile
Onsite
Offshore
4 Months
AWS Engineer
1
3
Time lines ::
4 Months
Total Resources ::
6 person months
12 person months
Cloud Architect
0.5
MS1
MS2
MS3
M8
M9
M10
MS1
AWS Account setup
AWS LAN network setup
Establish On-Premises to AWS connectivity (VPN)
MS2
AWS – EC2 AMI setup
AWS – Foundation services setup (AD, DNS, Patching, Antivirus, monitoring, logging, backup)
AWS Identity federation
AWS KMS and encryption policies setup
Deploy Development / Test workloads
MS3
Establish On premises to AWS Connectivity (Direct connect)
Setup EC2 provisioning via Infrastructure as a code
Control policies and scripts setup for cost optimization
Build validation, testing and signoff
Deploy Production workloads

## Slide 12
Phase II - Work stream 4 & 5 – PaaS & CaaS – Activities
TCS – Fifth Third Bank Confidential
S.No | Module | Activities
1 | PaaS / CaaS (Platform build) | Build PaaS infrastructure Configure Container / PaaS orchestration module Setup private Image repository (for containers), build and image streams Configure replication controllers (for PaaS service instances) Configure data persistence layer & Application routers HA configuration for PaaS platform Configure namespaces, projects and user accounts Configure management console Configure monitoring and log integration Build technology stack (Web tier, App tier, Database tier etc.)

## Slide 13
Phase II - Work stream 4 & 5 – PaaS & CaaS – Timelines, Resources
TCS – Fifth Third Bank Confidential
Activity Stream
Estimated Timelines
Resourcing (per activity stream/ module)
Module 2 : PaaS & CaaS – Build & Deploy
Resource Profile
Onsite
Offshore
Application Consultant
2
4
Time lines ::
6 Months
Resources ::
15 person months
24 person months
6 Months
DevOps Engineer
MS1
MS2
M9
M12
MS1
PaaS platform build
CaaS platform build
Image repository setup & image streams deployed
Management console setup
MS2
HA configuration
Integration
Technology stack build (Web, App, database, MQ)
0.5

## Slide 14
Hybrid Cloud – Phase II – Timelines, Resources – Total Estimate
TCS – Fifth Third Bank Confidential
Work Stream
Estimated Project Timelines
Resources
WS 1: Infrastructure as a Code
Resource Profile
Onsite
Offshore
6 Months
Automation Architect
0.5
-
Automation Engineer
1
3
WS 2 : Private Cloud Platform Build
4 Months
Cloud engineer
1
3
WS 3 : AWS Build
4 Months
Cloud Architect
0.5
AWS Engineer
1
3
Application Consultant
0.5
DevOps Engineer
2
4
WS 4 & 5 : PaaS & CaaS Build
6 Months
Total Resources:
7.5
15
Process Consultant
0.25
0.5
Process Consultant
0.75
1.5